## Dashboard
CAPA MANAGEMENT DASHBOARD
Real-time overview of Corrective and Preventive Actions
KEY PERFORMANCE INDICATORS
| Total Open | Overdue | Closed (Total) |  | Avg Days to Close
| 2 | 3 | 2 |  | 41.5
STATUS BREAKDOWN |  |  | SOURCE ANALYSIS
Open | 1 |  | Customer Complaint | 1
In Progress | 1 |  | Internal Audit | 1
Pending Verification | 1 |  | External Audit | 0
Closed | 2 |  | Nonconformance | 1
|  |  | PMS/Vigilance | 0
PRIORITY BREAKDOWN |  |  | Supplier Issue | 1
Critical | 1 |  | Process Deviation | 1
High | 1 |  | Management Review | 0
Medium | 2
Low | 1
EFFECTIVENESS RATE
Effective | 2
Partially Effective | 0
Not Effective | 0
Pending | 3
📋 Enter CAPA data in the 'Log' sheet. Dashboard updates automatically.

## Log
CAPA # | Date Opened | Description | Source | Priority | Target Date | Status | Owner | Date Closed | Days Open | Effectiveness | Notes
CAPA-2025-001 | 2025-01-02 | Incorrect labeling on product UC-200 | Customer Complaint | High | 2025-02-15 | Closed | M. Schmidt | 2025-02-10 | 39 | Effective | Root cause: SOP gap. Corrected.
CAPA-2025-002 | 2025-01-08 | Supplier material OOS | Supplier Issue | Medium | 2025-03-01 | In Progress | T. Weber |  | 373 | Pending | Awaiting supplier response
CAPA-2025-003 | 2025-01-10 | Calibration deviation on Test Equipment TE-045 | Nonconformance | Low | 2025-02-28 | Pending Verification | S. Braun |  | 371 | Pending | Actions complete, verifying effectiveness
CAPA-2025-004 | 2025-01-15 | Documentation error in DHF | Internal Audit | Medium | 2025-03-15 | Open | K. Hoffmann |  | 366 | Pending | Investigation ongoing
CAPA-2025-005 | 2024-12-01 | Critical process parameter drift | Process Deviation | Critical | 2025-01-15 | Closed | M. Schmidt | 2025-01-14 | 44 | Effective | Process revalidated
Formulas:
Days Open = IF([Status]="Closed",IF([Date Closed]<>"",[Date Closed]-[Date Opened],""),TODAY()-[Date Opened])

## Instructions
CAPA LOG - USER INSTRUCTIONS
HOW TO USE THIS WORKBOOK
1. LOG SHEET
• Enter all CAPAs in the Log sheet
• CAPA # format: CAPA-YYYY-XXX (e.g., CAPA-2025-017)
• IMPORTANT: Enter dates by selecting the cell and using date picker
• Or type dates as: 2025-01-15 (Excel will convert to date)
• Select Status from: Open, In Progress, Pending Verification, Closed
• Select Priority from: Critical, High, Medium, Low
• Days Open calculates automatically
2. DASHBOARD
• All KPIs update automatically based on Log data
• Overdue = Target Date passed AND Status ≠ Closed
3. STATUS DEFINITIONS
• Open: CAPA initiated, investigation not started
• In Progress: Investigation/actions underway
• Pending Verification: Actions complete, awaiting effectiveness check
• Closed: Effectiveness verified, CAPA complete
4. PRIORITY DEFINITIONS
• Critical: Patient safety impact, immediate action required
• High: Regulatory impact, major quality issue
• Medium: Moderate impact, standard timeline
• Low: Minor issue, improvement opportunity
5. EFFECTIVENESS OPTIONS
• Effective: Root cause eliminated, no recurrence
• Partially Effective: Improvement observed, monitoring continues
• Not Effective: Issue recurred, new CAPA required
• Pending: Not yet evaluated
6. TIPS
• Use filters in Log sheet to find specific CAPAs
• Red highlight on Target Date = OVERDUE
• Review Dashboard weekly in team meetings
• Use dropdown menus for consistent data entry
─────────────────────────────────────────────────────
Template provided by QCore Consulting ¦ qcore-consulting.de
Compliant with ISO 13485:2016 and FDA 21 CFR 820.100

## Dropdowns (hidden)
Status | Priority | Source | Effectiveness
Open | Critical | Customer Complaint | Effective
In Progress | High | Internal Audit | Partially Effective
Pending Verification | Medium | External Audit | Not Effective
Closed | Low | Nonconformance | Pending
PMS/Vigilance
Supplier Issue
Process Deviation
Management Review
Other